## Blad1
Symbols:
Month | December | [16 empty] | January | [7 empty] | Adam | A
Week | 50 |  |  |  |  | 51 |  |  |  |  | 52 |  |  |  |  | 1 |  |  |  |  | 2 |  |  |  |  | Emma | E
Date | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 |  | Claudia | C
[26 empty] | Isabel | I
[26 empty] | Natalia | N
planning: UML, Gantt, text-plan, group contract, sketches, github rep. | all | all | all | all | all | all | 80% complete | [18 empty] | holidays
html: simple structure with all IDs (needed for css and ts) | [7 empty] | 0% complete | [17 empty] | in progress
complete
milestone
html: continued | [11 empty] | 0% complete
css | [11 empty] | 0% complete
typescript: all classes(interfaces) with properties and empty methods | [6 empty] | 0% complete
typescript: continued | [21 empty] | 0% complete
canvas basic elements shapes | [10 empty] | 0% complete
canvas: continued | [21 empty] | 0% complete
typescript: classes implementation
typescript: continued | [21 empty] | 0% complete
reconciliation(avstämning) milestone | [14 empty] | all | 0% complete
idea presentation milestone | [5 empty] | all | 0% complete
presentation (inlämning) milestone | [23 empty] | all | 0% complete
merge ? | [7 empty] | all |  |  | all |  |  |  | all |  |  |  | all
internal release? | [22 empty] | 0%complete
testing and bugfixing | [22 empty] | 0%complete